## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-001 | As a Salesforce Administrator, I want to provision a new Salesforce Trial Org and convert it to Production with 2 Admin licenses, so that the BusinessConnect implementation can begin in a production-ready environment. | Requirement: BR1 - Salesforce Org setup Phase: Phase 1 This story covers the initial Salesforce org provisioning including trial org creation, conversion to production, provisioning of 2 admin licenses per SOW, creation of full sandbox, and user creation for technical team. Dependencies: None - this is the first step Assumptions: Salesforce licensing agreements are in place | Configuration | • Given the project has been initiated, When the Salesforce Trial Org is provisioned, Then the org should be successfully created and accessible • Given the Trial Org is provisioned, When the conversion to Production is completed, Then the org should be converted to Production status with full capabilities • Given the Production org is ready, When 2 Admin licenses are provisioned, Then both admin licenses should be active and assignable • Given the Production org exists, When a full Sandbox is created, Then the Sandbox should be a complete copy of Production and accessible for testing • Given the Sandbox is created, When technical team users are created, Then all users should have appropriate access for configuration and development work
US-002 | As a Salesforce Administrator, I want to install BusinessConnect package v10.147 in the Sandbox environment, so that the credit management functionality is available for configuration. | Requirement: BR2 - BusinessConnect package install Phase: Phase 1 This story covers the installation of the specific BusinessConnect package version in the Sandbox environment. Dependencies: US-001 (Org setup must be complete) Assumptions: Package installation credentials and access provided by Equifax | Configuration | • Given the Sandbox environment is ready, When BusinessConnect package v10.147 is installed, Then the package should be successfully installed with all components and objects available • Given the package is installed, When the installation is verified, Then all BusinessConnect tabs, objects, and features should be accessible in the Sandbox
US-003 | As a Credit Administrator, I want to configure Equifax data providers with secure credentials in the Sandbox environment, so that the system can connect to Equifax services for credit reporting. | Requirement: BR3 - Data Provider and Data Provider Products configuration Phase: Phase 1 This story covers the configuration of multiple Equifax data providers including Equifax, Equifax Apigee, Equifax Business Principal Report, and Equifax Canada with their respective credentials and settings. Data Providers to configure: - Equifax (User ID: 999WM01393, Security Code: TR, Environment: gptest) - Equifax Apigee (User ID: 999WM01393) - Equifax Business Principal Report - Equifax Canada (User ID: 999WM00178, Security Code: TR, Subscriber Code: 7007) Dependencies: US-002 (BusinessConnect package must be installed) Assumptions: All credentials will be sent via secure email at UAT time Note: Credentials shown are for UAT environment | Configuration | • Given BusinessConnect is installed, When Equifax data provider is configured with User ID 999WM01393 and Security Code TR in gptest environment, Then the data provider should be active and able to connect to Equifax services • Given BusinessConnect is installed, When Equifax Apigee data provider is configured with User ID 999WM01393, Then the data provider should be active and able to connect to Equifax Apigee services • Given BusinessConnect is installed, When Equifax Business Principal Report data provider is configured, Then the data provider should be active and ready for BPR report pulls • Given BusinessConnect is installed, When Equifax Canada data provider is configured with User ID 999WM00178, Security Code TR, and Subscriber Code 7007, Then the data provider should be active and able to connect to Equifax Canada services
US-004 | As a Credit Administrator, I want to configure Data Provider Products for all Equifax report types in the Sandbox, so that specific credit reports can be pulled through BusinessConnect. | Requirement: BR3 - Data Provider Products configuration Phase: Phase 1 This story covers the configuration of the following Data Provider Products: - Equifax Commercial Credit (BCIR2.0+ with OneScore 2037) - RPT0036 with SCR2037 - Equifax Business TIN Match - Equifax Business Verification - RPT0042 - Equifax Business Verification with TIN Match - Equifax Business Principal Report - RPT2001 with Fico10 - Equifax Canada Commercial Credit Each product requires specific product codes and option packages to be configured. Dependencies: US-003 (Data Providers must be configured first) Assumptions: Product codes and option packages are standard Equifax configurations | Configuration | • Given Equifax data provider is configured, When Equifax Commercial Credit product is configured with RPT0036 and SCR2037 (OneScore 2037), Then the product should be available for BCIR2.0 report pulls • Given Equifax Apigee is configured, When Equifax Business TIN Match product is configured, Then the product should be available for TIN matching • Given Equifax Apigee is configured, When Equifax Business Verification product is configured with RPT0042, Then the product should be available for business verification report pulls • Given Equifax Apigee is configured, When Equifax Business Verification with TIN Match product is configured, Then the product should be available for combined verification and TIN matching • Given Equifax data provider is configured, When Equifax Business Principal Report product is configured with RPT2001 and Fico10, Then the product should be available for BPR report pulls • Given Equifax Canada is configured, When Equifax Canada Commercial Credit product is configured, Then the product should be available for Canadian credit report pulls
US-005 | As a Salesforce Administrator, I want to create 13 custom fields on the Account object, so that business verification data and decision information can be captured and stored. | Requirement: BR4 - Account Page fields creation Phase: Phase 1 This story covers the creation of the following custom fields on the Account object: 1. Business_Name__c (Text) 2. BillingStreet (Text Area) - standard field 3. BillingCity (Text) - standard field 4. BillingState (Text) - standard field 5. BillingPostalCode (Text) - standard field 6. BillingCountry (Picklist) - standard field 7. BVS_Tax_ID__c (Text) 8. Owner_First_Name__c (Text) 9. Owner_Last_Name__c (Text) 10. Decision_Flag__c (Text) - values: 'charge card account' or 'trade credit account' 11. BVS_Decision__c (Text) - values: 'Approve', 'Manual Review', or 'Decline' 12. BVI_Score__c (Number) 13. Fraud_Alert_Score__c (Number) Dependencies: US-002 (BusinessConnect must be installed) Assumptions: Standard billing fields may already exist and only need to be verified Note: These fields must be created before any development or integration work begins | Configuration | • Given the Account object exists, When Business_Name__c text field is created, Then the field should be available on the Account object for data entry • Given the Account object exists, When BVS_Tax_ID__c text field is created, Then the field should be available to store Tax ID information • Given the Account object exists, When Owner_First_Name__c and Owner_Last_Name__c text fields are created, Then both fields should be available to store business owner information • Given the Account object exists, When Decision_Flag__c text field is created, Then the field should accept values 'charge card account' or 'trade credit account' • Given the Account object exists, When BVS_Decision__c text field is created, Then the field should accept values 'Approve', 'Manual Review', or 'Decline' • Given the Account object exists, When BVI_Score__c numeric field is created, Then the field should accept and store numeric values for BVI scores • Given the Account object exists, When Fraud_Alert_Score__c numeric field is created, Then the field should accept and store numeric values for fraud alert scores • Given all custom fields are created, When the Account page layout is updated, Then all new fields should be visible and accessible on the Account page
US-006 | As a Credit Administrator, I want to configure two Credit Policies (Equifax Commercial and Equifax Canada) in BusinessConnect, so that appropriate credit products can be selected for manual and automated credit pulls. | Requirement: BR6 - Credit Policies configuration Phase: Phase 1 This story covers the configuration of: 1. Equifax Commercial credit policy (Default Policy: Y) - used for Equifax Commercial Credit and BPR reports 2. Equifax Canada credit policy - used for Equifax Canada Commercial Credit reports Each policy must be configured with appropriate products for Verification, Credit Prequalification, and Credit Review steps. Dependencies: US-004 (Data Provider Products must be configured), US-005 (Account fields must be created) Assumptions: Credit policy rules follow standard BusinessConnect configuration patterns | Configuration | • Given Data Provider Products are configured, When Equifax Commercial credit policy is created and set as Default Policy, Then the policy should be available for selection and automatically assigned to accounts without explicit policy assignment • Given Equifax Commercial policy exists, When products are assigned for Verification, Prequalification, and Credit Review steps, Then the appropriate Equifax products should be selectable for each step • Given Data Provider Products are configured, When Equifax Canada credit policy is created, Then the policy should be available for selection for Canadian accounts • Given Equifax Canada policy exists, When Equifax Canada Commercial Credit product is assigned, Then the product should be available for Canadian credit report pulls
US-007 | As a Credit User, I want three manual buttons on the Account page ('Review Credit', 'Review BPR', 'Business Verification'), so that I can manually pull credit reports when needed for trade credit accounts. | Requirement: BR5 - Manual workflow configuration Phase: Phase 1 This story covers the configuration of three buttons: 1. 'Review Credit' button - pulls BCIR 2.0/Canada Commercial reports 2. 'Review BPR' button - pulls Equifax Business Principal Reports (BPR) 3. 'Business Verification' button - pulls Business Verification reports Dependencies: US-006 (Credit Policies must be configured), US-005 (Decision_Flag__c field must exist) Assumptions: Users must select applicable credit policy prior to initiating manual report pulls. Training will be provided as part of SOW. Business Rules: Decision_Flag__c must equal 'Trade Credit Account' for manual pulls to work | Development | • Given a Credit Policy is selected on the Account and Decision_Flag__c equals 'Trade Credit Account', When the 'Review Credit' button is clicked, Then the system should initiate a pull for BCIR 2.0 or Canada Commercial report based on the selected policy • Given a Credit Policy is selected on the Account and Decision_Flag__c equals 'Trade Credit Account', When the 'Review BPR' button is clicked, Then the system should initiate a pull for Equifax Business Principal Report • Given a Credit Policy is selected on the Account and Decision_Flag__c equals 'Trade Credit Account', When the 'Business Verification' button is clicked, Then the system should initiate a pull for Business Verification report • Given Decision_Flag__c does not equal 'Trade Credit Account', When any manual button is clicked, Then the system should prevent the report pull and display an appropriate error message
US-008 | As a Credit User, I want to view Business Verification reports in the Equifax Business Verification Reports section on the Account page, so that I can review verification results and scores. | Requirement: BR7 - Report objects configuration for Business Verification Phase: Phase 1 This story covers the configuration to display Business Verification reports in a dedicated section on the Account page, showing report details including BVI Score and Fraud Alert Score. Dependencies: US-005 (Account fields must be created), US-007 (Manual buttons must be configured) Assumptions: Report data is parsed and stored according to BusinessConnect standard parsing logic | Development | • Given a Business Verification report has been pulled for an Account, When the Account page is viewed, Then the report should be visible in the Equifax Business Verification Reports section • Given a Business Verification report exists, When the report is opened, Then all verification details including BVI Score and Fraud Alert Score should be displayed
US-009 | As a Credit User, I want to view BCIR2.0+ reports in the Equifax Commercial Reports section on the Account page, so that I can review commercial credit information and OneScore. | Requirement: BR7 - Report objects configuration for BCIR2.0+ Phase: Phase 1 This story covers the configuration to display BCIR2.0+ reports with OneScore 2037 in the Equifax Commercial Reports section on the Account page. Dependencies: US-005 (Account fields must be created), US-007 (Manual buttons must be configured) Assumptions: Report data includes OneScore 2037 as configured in the product option package | Development | • Given a BCIR2.0+ report has been pulled for an Account, When the Account page is viewed, Then the report should be visible in the Equifax Commercial Reports section with the OneScore displayed • Given multiple BCIR2.0+ reports exist for an Account, When the Equifax Commercial Reports section is viewed, Then all reports should be listed with Report ID, OneScore, and Created Date
US-010 | As a Credit User, I want to view Business Principal Reports (BPR) in the Equifax Blended Reports section on the Account page, so that I can review blended credit information including FICO scores. | Requirement: BR7 - Report objects configuration for BPR Phase: Phase 1 This story covers the configuration to display Business Principal Reports in the Equifax Blended Reports section on the Account page. Dependencies: US-005 (Account fields must be created), US-007 (Manual buttons must be configured) Assumptions: BPR reports include Fico10 score as configured in the product option package | Development | • Given a BPR report has been pulled for an Account, When the Account page is viewed, Then the report should be visible in the Equifax Blended Reports section • Given a BPR report exists, When the report is opened, Then all blended credit information including FICO score should be displayed
US-011 | As a Credit User, I want to view Canada Commercial Credit reports in the Equifax Commercial Canada Reports section on the Account page, so that I can review Canadian business credit information. | Requirement: BR7 - Report objects configuration for Canada Phase: Phase 1 This story covers the configuration to display Canada Commercial Credit reports in a dedicated section on the Account page for Canadian accounts. Dependencies: US-005 (Account fields must be created), US-007 (Manual buttons must be configured) Assumptions: Reports are pulled using Equifax Canada data provider and credit policy | Development | • Given a Canada Commercial Credit report has been pulled for an Account, When the Account page is viewed, Then the report should be visible in the Equifax Commercial Canada Reports section • Given a Canada report exists, When the report is opened, Then all Canadian credit information should be displayed in the appropriate format
US-012 | As a system, I want to configure a Business Verification scorecard that evaluates BVI Score and Fraud Alert Score, so that automated credit decisions can be rendered based on defined business rules. | Requirement: BR8 - Business Verification scorecard configuration Phase: Phase 1 This story covers the configuration of a scorecard with decision rules based on BVI Score and Fraud Alert Score ranges. The scorecard evaluates scores and populates BVS_Decision__c field with 'Auto Approve', 'Manual Review', or 'Decline'. Scorecard Decision Matrix (from BRD image16.png): - BVI 80-100 + Fraud >=201: Auto Approve - BVI 80-100 + Fraud <=200: Manual Review - BVI 80-100 + Fraud null: Manual Review - BVI 50-79 + Fraud >=201: Manual Review - BVI 50-79 + Fraud <=200: Manual Review - BVI 50-79 + Fraud null: Manual Review - BVI <50 + Fraud >=201: Manual Review - BVI <50 + Fraud <=200: Decline - BVI <50 + Fraud null: Decline Dependencies: US-005 (BVI_Score__c, Fraud_Alert_Score__c, and BVS_Decision__c fields must exist) Assumptions: Scorecard rules are final and approved by business stakeholders Note: Do not assume or use any score-related names from the system - use exact field names as defined | Development | • Given a Business Verification report is completed with BVI Score between 80-100 and Fraud Alert Score >=201, When the scorecard is executed, Then BVS_Decision__c should be set to 'Auto Approve' • Given a Business Verification report is completed with BVI Score between 80-100 and Fraud Alert Score <=200, When the scorecard is executed, Then BVS_Decision__c should be set to 'Manual Review' • Given a Business Verification report is completed with BVI Score between 80-100 and Fraud Alert Score is null, When the scorecard is executed, Then BVS_Decision__c should be set to 'Manual Review' • Given a Business Verification report is completed with BVI Score between 50-79 and any Fraud Alert Score value, When the scorecard is executed, Then BVS_Decision__c should be set to 'Manual Review' • Given a Business Verification report is completed with BVI Score <50 and Fraud Alert Score >=201, When the scorecard is executed, Then BVS_Decision__c should be set to 'Manual Review' • Given a Business Verification report is completed with BVI Score <50 and Fraud Alert Score <=200, When the scorecard is executed, Then BVS_Decision__c should be set to 'Decline' • Given a Business Verification report is completed with BVI Score <50 and Fraud Alert Score is null, When the scorecard is executed, Then BVS_Decision__c should be set to 'Decline'
US-013 | As a system, I want to process incoming API requests from MM2.0 to create Account records, pull credit reports, execute scorecards, and return decisions, so that automated credit decisioning can be performed via API integration. | Requirement: BR9 - Automated flow/API integration Phase: Phase 1 This story covers the end-to-end automated API integration flow as detailed in the 'mSupply BusinessConnect API Integration Design Document'. Key Integration Stages: 1. Initiation: MM2.0 invokes Salesforce to create new Account record 2. Processing: Salesforce performs internal validations, pulls credit reports, executes scorecard 3. Response: Salesforce syncs Account ID, Decision (BVS_Decision__c), BVI Score, and Fraud Alert Score back to ERP The integration includes authentication mechanisms, error handling, and specific request/response payloads. Dependencies: US-005 (Account fields must exist), US-008 (Report configuration must be complete), US-012 (Scorecard must be configured) Assumptions: API Integration Design Document has been reviewed and approved by client within first week after project kick-off (per BR Assumption #1) Note: Detailed technical specifications are in the separate API Integration Design Document | Development | • Given MM2.0 sends a valid API request with business information, When Salesforce receives the request, Then a new Account record should be created with all provided data populated in the appropriate fields • Given an Account record is created via API, When internal validations pass and Decision_Flag__c equals 'Trade Credit Account', Then the system should automatically pull a Business Verification report • Given a Business Verification report is completed, When the scorecard is executed, Then BVS_Decision__c, BVI_Score__c, and Fraud_Alert_Score__c fields should be populated based on scorecard rules • Given the scorecard execution is complete, When the processing is finished, Then the system should send a response to MM2.0 containing Account ID, BVS_Decision__c value, BVI_Score__c value, and Fraud_Alert_Score__c value • Given an error occurs during processing, When the error is encountered, Then the system should return an appropriate error response to MM2.0 with error details
US-014 | As a Salesforce Administrator, I want to provision the remaining BusinessConnect licenses per the SOW, so that all users have appropriate access to the system. | Requirement: BR10 - BusinessConnect licenses provisioning Phase: Phase 1 This story covers the provisioning of all licenses as specified in the SOW: - Credit User licenses: 8 - API licenses: 2 - Sandbox licenses: 10 Note: 2 Admin licenses were already provisioned in US-001. Dependencies: US-001 (Initial org setup must be complete) Assumptions: License allocation aligns with SOW agreement and user requirements | Configuration | • Given the Salesforce org is provisioned, When 8 Credit User licenses are provisioned, Then all 8 licenses should be active and assignable to credit users • Given the Salesforce org is provisioned, When 2 API licenses are provisioned, Then both API licenses should be active and available for API integration users • Given the Salesforce org is provisioned, When 10 Sandbox licenses are provisioned, Then all 10 licenses should be active and assignable for sandbox testing
US-015 | As an Ascendion Business Analyst, I want to review and approve all test cases before UAT begins, so that test coverage is comprehensive and aligned with business requirements. | Enterprise Mandate: Ascendion mandatory test case review and BA signoff Phase: Phase 1 This is a governance story ensuring quality assurance through mandatory test case review by Ascendion BA before user acceptance testing begins. Dependencies: All functional user stories (US-001 through US-014) must be developed Assumptions: Test cases will be created covering all acceptance criteria from functional user stories | Governance | • Given all functional development is complete, When test cases are created for all user stories, Then the Ascendion Business Analyst should review each test case for completeness and accuracy • Given test cases are reviewed, When any gaps or issues are identified, Then the BA should document required changes and request revisions • Given all test cases meet requirements, When the BA review is complete, Then the BA should provide formal signoff approval to proceed to UAT
US-016 | As a Project Manager, I want to receive advance notification from Equifax admin for any planned configuration changes, so that stakeholders can prepare and coordinate accordingly. | Enterprise Mandate: Advance notification for planned configuration changes from Equifax admin Phase: Phase 1 This is a governance story ensuring proper communication and change management for any configuration changes planned by the Equifax administration team. Dependencies: Project communication protocols must be established Assumptions: Notification timeline will be agreed upon during project kickoff | Governance | • Given a configuration change is planned by Equifax admin, When the change is scheduled, Then advance notification should be sent to all project stakeholders with details of the change and timeline • Given advance notification is sent, When stakeholders receive the notification, Then they should have sufficient time to review and prepare for the configuration change impact
US-017 | As a Development Lead, I want final code review support and coding signoff from the Equifax team, so that code quality and best practices are validated before deployment. | Enterprise Mandate: Final code review support for coding signoff from Equifax team Phase: Phase 1 This is a governance story ensuring code quality through mandatory review and signoff by the Equifax technical team before any code is deployed to production. Dependencies: All development user stories (US-007 through US-013) must be completed Assumptions: Equifax team will provide timely code review within agreed SLA | Governance | • Given all development work is complete, When code is ready for review, Then the Equifax team should conduct a comprehensive code review covering functionality, security, and best practices • Given code review is complete, When all issues are resolved and code meets quality standards, Then the Equifax team should provide formal coding signoff approval
US-018 | As a QA Lead, I want production-like test data covering all scenarios from the Equifax team, so that comprehensive testing can be performed in the Sandbox environment. | Enterprise Mandate: Provision of production-like test data covering all scenarios from Equifax team Phase: Phase 1 This is a governance story ensuring adequate test data is available for all testing scenarios including positive, negative, and edge cases. Test data should cover: - Various BVI Score ranges (80-100, 50-79, <50) - Various Fraud Alert Score ranges (>=201, <=200, null) - Different account types (Trade Credit Account, Charge Card Account) - All report types (BVS, BCIR2.0+, BPR, Canada) - Error scenarios and edge cases Dependencies: US-002 (Sandbox must be ready), US-004 (Data Provider Products must be configured) Assumptions: Equifax will provide test data that mirrors production scenarios without exposing real customer data | Governance | • Given the Sandbox environment is configured, When test data is needed for UAT, Then the Equifax team should provide production-like test data covering all scorecard decision scenarios • Given test data is provided, When testing is performed, Then the test data should enable validation of all acceptance criteria across all functional user stories • Given test data is used, When edge cases and error scenarios are tested, Then appropriate test data should be available to validate system behavior
US-019 | As a Deployment Manager, I want to validate release readiness, execute deployment to Production, and perform post-deployment verification, so that the solution is successfully deployed and operational. | Requirement: BR11 - Deployment Phase: Phase 1 This is a dedicated deployment story covering: 1. Pre-deployment validation and release readiness checks 2. Deployment execution from Sandbox to Production 3. Post-deployment verification and smoke testing 4. Creation and delivery of deployment guide document to client Deployment includes: - All configuration changes (fields, data providers, products, policies) - All custom development (buttons, API integration, scorecard) - All report configurations - License provisioning in Production Dependencies: All functional stories (US-001 through US-014), all governance stories (US-015 through US-018) must be complete with signoffs Assumptions: UAT signoff has been obtained before deployment to Production | Deployment | • Given all development and testing is complete with signoffs, When release readiness is assessed, Then all components should be validated as ready for Production deployment • Given release readiness is confirmed, When deployment to Production is executed, Then all configuration and code should be successfully deployed without errors • Given deployment is complete, When post-deployment verification is performed, Then all functionality should be tested and confirmed working in Production environment • Given deployment is verified, When smoke testing is complete, Then a deployment guide document should be created and provided to the client • Given Production is live, When users access the system, Then all manual and automated workflows should function as designed and tested in UAT
US-020 | As a Product Owner, I want clarification on Business Verification report availability timing in the automated flow, so that API response times and user expectations can be properly managed. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: In the automated API flow, when MM2.0 creates an Account and Salesforce pulls a Business Verification report, is the report pull synchronous (MM2.0 waits for the report and decision) or asynchronous (Salesforce responds immediately and processes the report in the background)? What is the expected response time SLA for the API? This clarification is needed to: - Design appropriate timeout handling - Set correct user expectations - Implement proper error handling for slow report responses - Define SLA commitments to the ERP system | Development
US-021 | As a Product Owner, I want clarification on handling scenarios where Business Verification reports are unavailable or fail, so that appropriate fallback logic and error handling can be implemented. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: What should happen in the automated flow if the Business Verification report pull fails or times out? Should the system: a) Return an error to MM2.0 and not create the Account? b) Create the Account but return a 'Pending' or 'Error' decision status? c) Attempt to pull an alternative report type? d) Queue the request for retry? This clarification is needed to: - Define error handling strategy - Ensure data consistency between Salesforce and MM2.0 - Prevent orphaned or incomplete records - Set appropriate retry logic | Development
US-022 | As a Product Owner, I want clarification on the validation rules for incoming API requests, so that data quality and security requirements are properly enforced. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: What specific validations should be performed on incoming API requests from MM2.0 before creating the Account record? For example: - Required fields validation (which fields are mandatory?) - Data format validation (Tax ID format, postal code format, etc.) - Business rule validation (valid country codes, state codes, etc.) - Duplicate checking (should we check for existing accounts with same Tax ID or business name?) This clarification is needed to: - Implement appropriate validation logic - Define clear error messages for validation failures - Prevent creation of invalid or duplicate records - Ensure data quality from the start | Development
US-023 | As a Product Owner, I want clarification on the Decision_Flag__c field population in the automated flow, so that the correct account type is set for scorecard processing. | Clarifying Question for BR4 and BR9 - Account Fields and Automated Flow Phase: Phase 1 Question: In the automated API flow, how is the Decision_Flag__c field populated? Does: a) MM2.0 send the Decision_Flag value in the API request? b) Salesforce automatically set it to 'Trade Credit Account' for all API-created accounts? c) Salesforce determine it based on other criteria or business logic? This clarification is needed because: - BR5 states Decision_Flag must equal 'Trade Credit Account' for manual workflows - BR9 automated flow needs to trigger Business Verification, which likely requires this flag - The scorecard and decision logic may depend on this field value | Development
US-024 | As a Product Owner, I want clarification on handling Canadian accounts in the automated flow, so that the correct credit policy and report types are used. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: In the automated API flow, how does the system determine whether to use Equifax Commercial or Equifax Canada credit policy? Is it based on: a) The BillingCountry field value? b) A specific flag sent by MM2.0 in the API request? c) Some other business logic? Also, should Canadian accounts pull Canada Commercial Credit reports instead of Business Verification reports, or should they pull both? This clarification is needed to: - Route accounts to the correct credit policy - Pull appropriate report types for Canadian vs US accounts - Ensure scorecard rules apply correctly for different geographies | Development
US-025 | As a Product Owner, I want clarification on the scorecard execution timing and field population sequence, so that the automated flow processes data in the correct order. | Clarifying Question for BR8 and BR9 - Scorecard and Automated Flow Phase: Phase 1 Question: In the automated flow, what is the exact sequence of operations? 1. Account created → Report pulled → Fields populated (BVI_Score__c, Fraud_Alert_Score__c) → Scorecard executed → BVS_Decision__c populated → Response sent? 2. Or is there a different sequence? Also, does the scorecard automatically execute when the Business Verification report is received, or does it need to be explicitly triggered? This clarification is needed to: - Design the correct process flow and triggers - Ensure fields are populated before scorecard evaluation - Prevent race conditions or null value errors - Optimize API response time | Development
US-026 | As a Product Owner, I want clarification on authentication and security requirements for the API integration, so that proper security controls are implemented. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: What authentication mechanism should be used for the MM2.0 to Salesforce API integration? a) OAuth 2.0? b) API Key? c) Named credentials? d) Other? Also: - Should API calls be restricted by IP address? - What level of encryption is required for data in transit? - Are there any specific compliance requirements (PCI, SOC2, etc.)? This clarification is needed to: - Implement appropriate authentication and authorization - Meet security and compliance requirements - Protect sensitive business and credit data - Configure proper API user permissions | Development
US-027 | As a Product Owner, I want clarification on error handling and retry logic for the API integration, so that transient failures are handled gracefully. | Clarifying Question for BR9 - Automated Flow Phase: Phase 1 Question: What should happen when transient errors occur (network timeouts, temporary service unavailability, etc.)? - Should MM2.0 implement retry logic, or should Salesforce handle retries? - How many retries should be attempted? - What is the retry interval? - Should failed requests be logged for manual review? - Should notifications be sent when requests fail after all retries? This clarification is needed to: - Design robust error handling - Prevent data loss from transient failures - Define monitoring and alerting requirements - Set clear expectations for system reliability | Development