## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-WEF-001 | As a system administrator, I want to configure the Credit Policy to support the new Paynet Report generation approach so that Paynet reports can be retrieved using the getListOfSimilars method with specified Account fields | Update Credit Policy configuration to enable Paynet Report generation using the new getListOfSimilars approach. This configuration change must be completed before development work begins on PaynetReportBatch class modifications. The Credit Policy must support report retrieval based on Name, BillingStreet, BillingCity, BillingState, BillingPostalCode, and BillingCountry fields from Account records. Dependencies: None Assumptions: Credit Policy configuration supports custom data provider product setup for Paynet; existing Credit Policy structure can accommodate the new retrieval method. Changes: New Credit Policy configuration for Paynet Report generation using getListOfSimilars method. | Configuration | Given the Credit Policy configuration page is accessed, When the administrator configures Paynet as a data provider product, Then the Credit Policy should allow selection of getListOfSimilars as the report retrieval method ¦ Given the Credit Policy is configured for Paynet, When the configuration specifies Account fields (Name, BillingStreet, BillingCity, BillingState, BillingPostalCode, BillingCountry), Then these fields should be stored as the data source for report generation ¦ Given the Credit Policy configuration is saved, When a validation check is performed, Then the system should confirm that all six required Account fields are mapped correctly
US-WEF-002 | As a BusinessConnect system, I want to modify the PaynetReportBatch class to replace the existing Paynet Report generation service call with the new getListOfSimilars approach so that Paynet Reports are retrieved using only specified Account fields | Modify the existing PaynetReportBatch class to update the Paynet Report generation logic. Replace the current service call implementation with the new getListOfSimilars approach that considers only Name, BillingStreet, BillingCity, BillingState, BillingPostalCode, and BillingCountry from Account Information. The existing rules calculation functionality within PaynetReportBatch must remain operational and unaffected unless compatibility updates are required. Dependencies: US-WEF-001 (Credit Policy configuration must be completed first) Assumptions: getListOfSimilars API is available and functional; Account records contain populated values for the six required fields; existing rules calculation logic is independent of report retrieval method. Changes: Code modification in PaynetReportBatch class - service call method replaced; new getListOfSimilars integration implemented. | Development | Given an Account record with populated Name, BillingStreet, BillingCity, BillingState, BillingPostalCode, and BillingCountry fields, When the PaynetReportBatch class executes, Then the system should invoke the getListOfSimilars service call using only these six Account fields ¦ Given the getListOfSimilars service call returns a list of similar entities, When the batch processes the response, Then the Paynet Report should be generated and stored in the BusinessConnect database ¦ Given the PaynetReportBatch class is modified, When the batch job completes execution, Then the existing rules calculation functionality should execute successfully without errors ¦ Given the Credit Policy is configured for Paynet Report generation, When the PaynetReportBatch class retrieves the Credit Policy, Then the same Credit Policy configuration should be applied during report generation
US-WEF-003 | As a BusinessConnect system, I want to ensure that rules calculation functionality within PaynetReportBatch continues to operate correctly after the report generation service call modification so that business rules are applied consistently to generated Paynet Reports | Validate that the existing rules calculation logic within the PaynetReportBatch class remains functional and produces accurate results after the Paynet Report generation service call is replaced with the getListOfSimilars approach. Rules calculation should process the newly retrieved Paynet Reports and apply business logic as defined in the Credit Policy. Dependencies: US-WEF-002 (PaynetReportBatch modification must be completed) Assumptions: Rules calculation logic is compatible with reports retrieved via getListOfSimilars; business rules defined in Credit Policy are still applicable to new report format. Changes: Validation and potential compatibility updates to rules calculation logic. | Development | Given a Paynet Report is successfully retrieved using the getListOfSimilars approach, When the rules calculation logic executes, Then all business rules defined in the Credit Policy should be evaluated against the report data ¦ Given the rules calculation completes, When the results are compared to expected outcomes based on Credit Policy rules, Then the calculated values should match the expected results ¦ Given multiple Account records are processed in the batch, When rules calculation is performed for each Paynet Report, Then each report should have rules applied independently and accurately
US-WEF-004 | As a QA analyst, I want to validate the modified PaynetReportBatch class with comprehensive test scenarios covering all Account field combinations so that the new getListOfSimilars approach functions correctly across different data conditions | Execute comprehensive testing of the modified PaynetReportBatch class to ensure the getListOfSimilars approach works correctly with various combinations of Account field data. Testing must cover scenarios including complete data, partial data, missing fields, and edge cases. Validation should confirm that Credit Policy is correctly applied and rules calculation produces accurate results. Dependencies: US-WEF-002 and US-WEF-003 (Development work must be completed) Assumptions: Test environment mirrors production configuration; test data is available for all scenarios. Changes: None - testing and validation phase. | Development | Given Account records with all six required fields populated, When the PaynetReportBatch executes, Then Paynet Reports should be successfully retrieved and rules calculation should complete without errors ¦ Given Account records with missing or null values in one or more required fields, When the PaynetReportBatch executes, Then the system should handle the scenario gracefully with appropriate error logging ¦ Given the batch processes multiple Account records with varying data quality, When the execution completes, Then a summary report should show successful retrievals, failures, and rules calculation results for each Account
US-WEF-005 | As a business analyst, I want to receive mandatory test case review and signoff confirmation from Ascendion so that all test scenarios are validated and approved before deployment | Ascendion team must review all test cases, test results, and validation documentation for the PaynetReportBatch modification. Business Analyst signoff is required to confirm that all business requirements have been met and testing is comprehensive. Dependencies: US-WEF-004 (Testing must be completed) Assumptions: Ascendion team is available for review; all test documentation is prepared and accessible. Changes: None - governance checkpoint. | Governance | Given all test cases and test results are documented, When the Ascendion team reviews the documentation, Then they should provide written confirmation of test case completeness ¦ Given the Business Analyst reviews test outcomes, When all business requirements are validated, Then the BA should provide formal signoff approval ¦ Given any issues or gaps are identified during review, When the Ascendion team documents findings, Then the development team should address all findings before proceeding to deployment
US-WEF-006 | As an Equifax administrator, I want to provide advance notification of the planned PaynetReportBatch configuration changes so that all stakeholders are informed and prepared for the update | Equifax admin team must provide advance notification to all stakeholders regarding the planned configuration changes to PaynetReportBatch class and Credit Policy updates. Notification should include change details, expected impact, timeline, and any required actions from stakeholders. Dependencies: US-WEF-005 (Test case review and BA signoff must be completed) Assumptions: Stakeholder communication channels are established; notification timeline allows adequate preparation time. Changes: None - governance checkpoint. | Governance | Given the deployment is scheduled, When the Equifax admin prepares the notification, Then it should include change details, impact assessment, timeline, and stakeholder action items ¦ Given the notification is sent, When stakeholders receive the communication, Then they should acknowledge receipt at least 48 hours before the planned deployment ¦ Given stakeholders have questions or concerns, When they respond to the notification, Then the Equifax admin should address all inquiries before deployment proceeds
US-WEF-007 | As an Equifax technical team member, I want to conduct final code review and provide coding signoff for the PaynetReportBatch modifications so that code quality and standards are validated before deployment | Equifax technical team must perform a comprehensive final code review of all PaynetReportBatch class modifications, Credit Policy configuration changes, and related code updates. Code review should validate adherence to coding standards, best practices, security requirements, and BusinessConnect integration guidelines. Formal coding signoff is required before deployment. Dependencies: US-WEF-005 (Test case review and BA signoff must be completed) Assumptions: Equifax team has access to all code repositories; code review checklist is available. Changes: None - governance checkpoint. | Governance | Given the PaynetReportBatch code modifications are submitted for review, When the Equifax technical team reviews the code, Then they should validate adherence to BusinessConnect coding standards and best practices ¦ Given the code review identifies any issues or improvement opportunities, When the Equifax team documents findings, Then the development team should address all critical and high-priority items before deployment ¦ Given all code review items are resolved, When the Equifax technical team completes their assessment, Then they should provide formal coding signoff approval
US-WEF-008 | As an Equifax data team member, I want to provide production-like test data covering all scenarios for PaynetReportBatch testing so that comprehensive validation can be performed before deployment | Equifax team must provision production-like test data that covers all testing scenarios for the PaynetReportBatch modification. Test data should include Account records with complete field data, partial data, missing fields, various geographic locations, and edge cases. Data must be representative of production conditions to ensure accurate testing. Dependencies: US-WEF-004 (Testing scenarios must be defined) Assumptions: Equifax team has access to production data patterns; test environment can accommodate production-like data volumes. Changes: None - governance checkpoint. | Governance | Given testing scenarios are defined, When the Equifax team provisions test data, Then the data should cover all positive, negative, and edge case scenarios ¦ Given the test data is loaded into the test environment, When the QA team validates data quality, Then the data should accurately represent production conditions ¦ Given testing is performed with the provisioned data, When results are analyzed, Then the data should enable comprehensive validation of all business requirements
US-WEF-009 | As a deployment manager, I want to execute release readiness checks, deployment validation, and post-deployment verification for the PaynetReportBatch modification so that the change is successfully deployed to production without issues | Execute comprehensive deployment activities including release readiness validation, deployment to production environment, and post-deployment verification. Ensure all governance checkpoints are completed, backup procedures are executed, deployment runbook is followed, and post-deployment smoke tests confirm successful implementation. Dependencies: US-WEF-005, US-WEF-006, US-WEF-007, US-WEF-008 (All governance stories must be completed) Assumptions: Deployment window is scheduled; rollback plan is prepared; production environment is accessible. Changes: None - deployment execution. | Deployment | Given all governance checkpoints are completed, When the deployment manager validates release readiness, Then all required approvals, notifications, and documentation should be confirmed complete ¦ Given the deployment to production is executed, When the PaynetReportBatch class and Credit Policy updates are deployed, Then the deployment should complete successfully without errors ¦ Given the deployment is complete, When post-deployment smoke tests are executed, Then the PaynetReportBatch should successfully retrieve Paynet Reports using the getListOfSimilars approach and rules calculation should execute correctly ¦ Given post-deployment validation is complete, When the deployment manager reviews all results, Then formal deployment completion signoff should be provided