## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-001 | As a Salesforce Administrator, I want to add the Equifax OneScore (SCR2038) data provider product and remove the CIDS (SCR0117) product in BusinessConnect configuration, so that the system uses the updated credit scoring product. | This story covers the configuration change to modify Data Provider products in BusinessConnect. The Equifax OneScore (SCR2038) must be added and Equifax Commercial Insight Delinquency Score (CIDS) (SCR0117) must be removed. This is a prerequisite for all subsequent development work. Assumption: Admin has access to BusinessConnect Data Provider configuration. Dependency: None. Clarifying Question: What is the timeline for decommissioning CIDS to ensure no active processes depend on it? | Configuration | • Given the BusinessConnect Data Provider configuration page is accessed, When the administrator adds Equifax OneScore (SCR2038) as a new data provider product, Then the product should be successfully saved and available for selection. • Given the BusinessConnect Data Provider configuration page is accessed, When the administrator removes Equifax Commercial Insight Delinquency Score (CIDS) (SCR0117), Then the product should no longer appear in the available data provider products list.
US-002 | As a Salesforce Administrator, I want to create the 'OneScore' field on Account, Decision, and Equifax Commercial Report objects, so that the OneScore value can be stored and displayed across these objects. | This story covers field creation for OneScore on three key objects: Account, Decision, and Equifax Commercial Report. Field specifications must follow Salesforce naming conventions and data type requirements. Assumption: Field data type is Number with appropriate precision. Dependency: US-001 must be completed. Clarifying Question: What is the exact data type, length, and decimal precision required for the OneScore field? | Configuration | • Given the Account object schema, When the 'OneScore' field is created with appropriate data type and precision, Then the field should be available for use in page layouts and automation. • Given the Decision object schema, When the 'OneScore' field is created with appropriate data type and precision, Then the field should be available for use in page layouts and automation. • Given the Equifax Commercial Report object schema, When the 'OneScore' field is created with appropriate data type and precision, Then the field should be available for use in page layouts and automation.
US-003 | As a Salesforce Administrator, I want to create the 'ScoreCard Type' field on Account, Decision, and Equifax Commercial Report objects, so that the type of scorecard used can be tracked and reported. | This story covers field creation for ScoreCard Type to distinguish between different scorecard types (e.g., Consumer Only vs. Commercial). Assumption: Field is a picklist or text field. Dependency: US-001 must be completed. Clarifying Question: What are the valid values for ScoreCard Type, and should it be a picklist or text field? | Configuration | • Given the Account object schema, When the 'ScoreCard Type' field is created with defined valid values, Then the field should be available for data entry and reporting. • Given the Decision object schema, When the 'ScoreCard Type' field is created with defined valid values, Then the field should be available for data entry and reporting. • Given the Equifax Commercial Report object schema, When the 'ScoreCard Type' field is created with defined valid values, Then the field should be available for data entry and reporting.
US-004 | As a Salesforce Administrator, I want to create the 'Fraud Victim Alert Indicator' field on the Consumer Report object with appropriate data provider product mapping, so that fraud victim alert data can be captured from the consumer report. | This story covers field creation and data provider mapping for the Fraud Victim Alert Indicator on the Consumer Report object. The field must be mapped to fetch values from the data provider. Assumption: Field is a checkbox or boolean type. Dependency: US-001 must be completed. Clarifying Question: What is the exact field name in the Equifax consumer report XML that should be mapped to this field? | Configuration | • Given the Consumer Report object schema, When the 'Fraud Victim Alert Indicator' field is created, Then the field should be available for data mapping. • Given the data provider product mapping configuration, When the mapping for 'Fraud Victim Alert Indicator' is configured, Then the field should automatically populate with values from the consumer report response.
US-005 | As a Salesforce Administrator, I want to create 'Fraud Victim Alert' and 'Active Duty Alert' fields on the Decision object, so that these alert statuses can be tracked for decision processing. | This story covers field creation for two alert-related fields on the Decision object. These fields will be used in pre-score rule processing. Assumption: Fields are checkbox or boolean type. Dependency: US-004 must be completed. Clarifying Question: Should these fields be auto-populated from Consumer Report or manually set during decision processing? | Configuration | • Given the Decision object schema, When the 'Fraud Victim Alert' field is created, Then the field should be available for use in decision workflows and rules. • Given the Decision object schema, When the 'Active Duty Alert' field is created, Then the field should be available for use in decision workflows and rules.
US-006 | As a Salesforce Administrator, I want to create checkbox fields 'PG Fraud Alert', 'PG Active Duty Alert', 'Onescore Consumer only', and 'Exceeds Comparable Limit' on the Decision object, so that credit analysts can view which rules were executed during decision processing. | This story covers the creation of viewed variable fields that serve as indicators for rule execution. These fields provide visibility to credit analysts on which business rules were triggered. Assumption: All fields are checkbox type. Dependency: US-005 must be completed. Clarifying Question: Should these fields be read-only for users or editable? | Configuration | • Given the Decision object schema, When the 'PG Fraud Alert' checkbox field is created, Then the field should be available on Decision page layouts for viewing rule execution status. • Given the Decision object schema, When the 'PG Active Duty Alert' checkbox field is created, Then the field should be available on Decision page layouts for viewing rule execution status. • Given the Decision object schema, When the 'Onescore Consumer only' checkbox field is created, Then the field should be available on Decision page layouts for viewing rule execution status. • Given the Decision object schema, When the 'Exceeds Comparable Limit' checkbox field is created, Then the field should be available on Decision page layouts for viewing rule execution status.
US-007 | As a Salesforce Administrator, I want to add the OneScore field to the Opportunity, Account (Relationship section), Equifax Commercial Report (Credit Information section), and Decision (Scorecard section) page layouts, so that users can view OneScore values in the appropriate context. | This story covers page layout modifications to display the OneScore field in four key locations as specified in the BRD. The field placement should match the current CIDS field placement pattern. Assumption: Page layouts are already configured with sections mentioned. Dependency: US-002 must be completed. Clarifying Question: Should the OneScore field replace the CIDS field in the same position, or be added as a new field? | Configuration | • Given the Opportunity page layout, When the OneScore field is added, Then users should be able to view the OneScore value on the Opportunity record. • Given the Account page layout, When the OneScore field is added to the Relationship section, Then users should be able to view the OneScore value in the Relationship section of the Account record. • Given the Equifax Commercial Report page layout, When the OneScore field is added to the Credit Information section, Then users should be able to view the OneScore value in the Credit Information section. • Given the Decision page layout, When the OneScore field is added to the Scorecard section, Then users should be able to view the OneScore value in the Scorecard section.
US-008 | As a Salesforce Administrator, I want to update the Decision scorecard configuration to replace the existing commercial scorecard with a new scorecard consisting of OneScore as the main component with Risk Rating and Primary Decision calculation, so that credit decisions are based on the new scoring model. | This story covers the scorecard configuration change in BusinessConnect to implement the new OneScore-based decision model. The new scorecard must include OneScore, Risk Rating, and Primary Decision calculation logic. Assumption: Scorecard configuration follows BusinessConnect standard setup. Dependency: US-002, US-007 must be completed. Clarifying Question: What are the specific Risk Rating thresholds and Primary Decision rules for the new OneScore-based scorecard? | Configuration | • Given the BusinessConnect scorecard configuration, When the new scorecard is created with OneScore as the main component, Then the scorecard should include Risk Rating and Primary Decision calculation logic. • Given a Decision record is processed, When the new scorecard is applied, Then the OneScore value should be used to calculate Risk Rating and Primary Decision according to defined business rules.
US-009 | As a system, I want to implement the PG Fraud Alert pre-score rule (Rule 4) in the OppConsumerController class, so that when any Personal Guarantor has a fraud victim alert on the Consumer report, the Secondary Decision is set to 'Manual Review'. | This story covers the implementation of Pre-Score Rule 4 for PG Fraud Alert. The rule checks if any Personal Guarantor (PG) has a fraud victim alert indicator set to true on their Consumer Report. If true, the Secondary Decision must be set to 'Manual Review' and the 'PG Fraud Alert' checkbox on Decision must be set to true. Assumption: Consumer Report data is available before this rule executes. Dependency: US-004, US-005, US-006 must be completed. Clarifying Question: Should this rule override any existing Secondary Decision value, or only set it if currently blank? | Development | • Given a Consumer Report for a Personal Guarantor is processed, When the Fraud Victim Alert Indicator is true on the Consumer Report, Then the Secondary Decision field on the Decision object should be set to 'Manual Review'. • Given the PG Fraud Alert rule is executed, When the rule condition is met, Then the 'PG Fraud Alert' checkbox on the Decision object should be set to true for visibility.
US-010 | As a system, I want to implement the PG Active Duty Alert pre-score rule (Rule 5) in the OppConsumerController class, so that when any Personal Guarantor has an active duty alert on the Consumer report, the Secondary Decision is set to 'Manual Review'. | This story covers the implementation of Pre-Score Rule 5 for PG Active Duty Alert. The rule checks if any Personal Guarantor has an active duty alert on their Consumer Report. If true, the Secondary Decision must be set to 'Manual Review' and the 'PG Active Duty Alert' checkbox on Decision must be set to true. Assumption: Consumer Report data is available before this rule executes. Dependency: US-004, US-005, US-006 must be completed. Clarifying Question: Should this rule override any existing Secondary Decision value, or only set it if currently blank? | Development | • Given a Consumer Report for a Personal Guarantor is processed, When the Active Duty Alert is true on the Consumer Report, Then the Secondary Decision field on the Decision object should be set to 'Manual Review'. • Given the PG Active Duty Alert rule is executed, When the rule condition is met, Then the 'PG Active Duty Alert' checkbox on the Decision object should be set to true for visibility.
US-011 | As a system, I want to move the Exceeds App Only Limit post-score rule (Rule 11) calculation from OppConsumerController class to PaynetReportBatch class, so that when Primary Decision is 'Approve' and Aggregate Exposure exceeds $500K, the Post-Score Action is set to 'Manual Review' with appropriate Secondary Decision value. | This story covers the refactoring of existing Rule 11 logic from OppConsumerController to PaynetReportBatch class. The rule checks if Primary Decision is 'Approve' and Aggregate Exposure > $500K, then sets Post-Score Action to 'Manual Review' and updates Secondary Decision to include the Primary Decision value. Assumption: Aggregate Exposure field exists and is populated. Dependency: US-008 must be completed. Clarifying Question: What is the exact format for the Secondary Decision value when this rule is triggered (e.g., 'Approve - Manual Review')? | Development | • Given the PaynetReportBatch class processes a Decision record, When Primary Decision is 'Approve' and Aggregate Exposure is greater than $500K, Then the Post-Score Action should be set to 'Manual Review'. • Given the Exceeds App Only Limit rule is triggered, When the conditions are met, Then the Secondary Decision should be updated to include the Primary Decision value.
US-012 | As a system, I want to implement the Exceeds Comparable Credit post-score rule (Rule 22) in PaynetReportBatch class, so that when Total Finance Amount exceeds $350K, Primary Decision is 'Approve', and Single Highest Credit is less than 50% of Equipment Cost, the Post-Score Action is set to 'Manual Review'. | This story covers the implementation of new Post-Score Rule 22 for Exceeds Comparable Credit. The rule uses Total_Finance_Amount__c from Opportunity, TotalCreditLimit from Equifax Commercial object, and Equipment_Cost__c from Opportunity. The calculation divides Single High Credit by Equipment Cost to determine percentage. A custom label should be used for the $350K threshold for configurability. The 'Exceeds Comparable Limit' checkbox on Decision must be set to true when triggered. Assumption: All required fields are populated before rule execution. Dependency: US-006, US-008 must be completed. Clarifying Question: What should happen if Equipment_Cost__c is zero or null to avoid division errors? | Development | • Given the PaynetReportBatch class processes a Decision record, When Total Finance Amount is greater than $350K and Primary Decision is 'Approve' and Single Highest Credit on BCIR is less than 50% of Equipment Cost, Then the Post-Score Action should be set to 'Manual Review'. • Given the Exceeds Comparable Credit rule is triggered, When the conditions are met, Then the Secondary Decision should be updated to include the Primary Decision value. • Given the Exceeds Comparable Credit rule is triggered, When the conditions are met, Then the 'Exceeds Comparable Limit' checkbox on the Decision object should be set to true. • Given the Total Finance Amount threshold, When the custom label is configured with value $350K, Then the rule should use this configurable value for comparison.
US-013 | As a system, I want to implement the OneScore Consumer Only post-score rule (Rule 23) in PaynetReportBatch class, so that when Primary Decision is 'Approve' and the OneScore is from a Consumer Only scorecard (no commercial data), the Post-Score Action is set to 'Manual Review'. | This story covers the implementation of new Post-Score Rule 23 for OneScore Consumer Only scenarios. The rule checks if the OneScore was calculated using only consumer data without commercial data from the Commercial report. The 'Onescore Consumer only' checkbox on Decision must be set to true when triggered. Assumption: There is an indicator field or method to determine if commercial data was used. Dependency: US-006, US-008 must be completed. Clarifying Question: How can the system determine if the OneScore is Consumer Only - is there a specific field or flag in the Commercial Report that indicates absence of commercial data? | Development | • Given the PaynetReportBatch class processes a Decision record, When Primary Decision is 'Approve' and the OneScore is calculated from Consumer Only scorecard with no commercial data, Then the Post-Score Action should be set to 'Manual Review'. • Given the OneScore Consumer Only rule is triggered, When the conditions are met, Then the 'Onescore Consumer only' checkbox on the Decision object should be set to true.
US-014 | As a developer, I want to comment out all CIDS-related code in CommercialReportBatch, PaynetReportBatch, and OppConsumerController classes, so that the system no longer processes CIDS score data as the product is being decommissioned. | This story covers the CML migration work to comment out CIDS-related code across multiple Apex classes. The following fields and references must be commented: CIDS_Score__c in CommercialReportBatch (mapping and exception handling), CIDS_Score__c in PaynetReportBatch (query), WEF_Score_Tier__c in PaynetReportBatch (query and mapping), WEF_Score_Tier__c in OppConsumerController (query and null assignment), CIDS_Score_Points__c in PaynetReportBatch (query), CIDS_Score_Points__c in CommercialReportBatch (query and mapping). Code should be commented with clear markers indicating CIDS decommissioning. Assumption: No active processes depend on CIDS fields. Dependency: US-001, US-008 must be completed. Clarifying Question: Should the commented code be removed entirely in a future release, or maintained as commented for audit purposes? | Development | • Given the CommercialReportBatch class, When CIDS_Score__c field references are commented out, Then the code should compile successfully and not attempt to map or process CIDS score values. • Given the PaynetReportBatch class, When CIDS_Score__c and CIDS_Score_Points__c field references in queries are commented out, Then the queries should execute without referencing these fields. • Given the PaynetReportBatch class, When WEF_Score_Tier__c field references are commented out, Then the code should not query or map WEF Score Tier values. • Given the OppConsumerController class, When WEF_Score_Tier__c field references are commented out, Then the code should not query or assign null values to WEF Score Tier. • Given all affected classes, When CIDS-related code is commented, Then clear comment markers should indicate the reason as 'CIDS being extinct' or 'CIDS decommissioning'.
US-015 | As a member of the Ascendion team, I want to ensure mandatory test case review and BA signoff is completed for all user stories, so that quality standards are met before deployment. | This is an enterprise mandate story covering the Ascendion requirement for mandatory test case review and Business Analyst signoff. All test cases must be reviewed and approved by the BA before any code is promoted to production. This ensures alignment with business requirements and quality standards. Assumption: Test cases are documented in the agreed format. Dependency: All development stories (US-009 through US-014) must be completed. | Governance | • Given all test cases are documented, When the Business Analyst reviews the test cases, Then formal signoff must be provided before proceeding to deployment. • Given test case review is completed, When any gaps or issues are identified, Then they must be resolved and re-reviewed before signoff.
US-016 | As a project stakeholder, I want to receive advance notification from the Equifax admin for any planned configuration changes, so that all parties are informed and can prepare accordingly. | This is an enterprise mandate story covering the requirement for advance notification of configuration changes from the Equifax admin team. This ensures transparency and allows stakeholders to plan for potential impacts. Assumption: A notification process and timeline are defined. Dependency: All configuration stories (US-001 through US-008) must be identified for notification. | Governance | • Given a configuration change is planned, When the Equifax admin prepares the change, Then advance notification must be sent to all relevant stakeholders with details of the change and timeline. • Given the notification is sent, When stakeholders receive it, Then they should have sufficient time to review and provide feedback before implementation.
US-017 | As a developer, I want to receive final code review support and coding signoff from the Equifax team, so that code quality and compliance standards are validated before deployment. | This is an enterprise mandate story covering the requirement for Equifax team code review and signoff. All custom code must be reviewed by the Equifax team for quality, security, and compliance before deployment to production. Assumption: Equifax team has capacity and process for code review. Dependency: All development stories (US-009 through US-014) must be completed. | Governance | • Given all custom code is completed, When the code is submitted for review, Then the Equifax team must conduct a thorough code review covering quality, security, and compliance aspects. • Given the code review is completed, When the Equifax team provides signoff, Then the code is approved for deployment to production.
US-018 | As a QA tester, I want the Equifax team to provide production-like test data covering all scenarios, so that comprehensive testing can be performed in non-production environments. | This is an enterprise mandate story covering the requirement for production-like test data from the Equifax team. Test data must cover all business scenarios including edge cases, positive and negative test cases, and various rule combinations. Assumption: Equifax team can provide anonymized production-like data. Dependency: All configuration and development stories must be completed before testing begins. | Governance | • Given testing is ready to begin, When the Equifax team provides test data, Then the data must be production-like and cover all identified test scenarios including edge cases. • Given the test data is provided, When testers use the data, Then all business rules and scenarios should be testable without requiring additional data.
US-019 | As a release manager, I want to ensure release readiness, deployment validation, and post-deployment checks are completed, so that the OneScore implementation is successfully deployed to production with minimal risk. | This is the deployment story covering release readiness assessment, deployment execution, validation, and post-deployment verification. This includes final checklist review, deployment plan execution, smoke testing, and production verification. Assumption: Deployment runbook and rollback plan are prepared. Dependency: All previous stories (US-001 through US-018) must be completed and signed off. | Deployment | • Given all user stories are completed and signed off, When the release readiness checklist is reviewed, Then all items must be verified as complete before deployment. • Given the deployment is executed, When the deployment completes, Then smoke testing must be performed to verify core functionality. • Given smoke testing passes, When post-deployment checks are performed, Then all configured fields, page layouts, and business rules must function as expected in production. • Given any deployment issues are identified, When the rollback plan is executed, Then the system must be restored to the previous stable state.