## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-001 | As a Salesforce Administrator, I want to provision a new Salesforce Trial Org and convert it to Production with 2 Admin licenses so that the mSupply BusinessConnect implementation can be deployed in a production-ready environment | This story covers the initial Salesforce environment setup including Trial Org provisioning, conversion to Production, Admin license allocation, Full Sandbox creation, and user creation for the technical team. Dependencies: None. Assumptions: Salesforce provisioning will be completed within standard timelines. | Configuration | • Given the project kickoff is complete, When the Salesforce Trial Org is provisioned, Then the org should be successfully created with admin access • Given the Trial Org is provisioned, When the conversion to Production is initiated, Then the org should be converted to Production status • Given the Production org is ready, When 2 Admin licenses are allocated, Then both licenses should be active and assignable • Given the Production org exists, When a Full Sandbox is created, Then the Sandbox should be fully synchronized with Production • Given the Sandbox is created, When technical team users are created, Then all users should have appropriate access permissions
US-002 | As a Salesforce Administrator, I want to install BusinessConnect package v10.147 in the Sandbox environment so that the credit management functionality is available for configuration and testing | This story covers the installation of the BusinessConnect managed package version 10.147 in the Sandbox environment. Dependencies: US-001 must be completed. Assumptions: Package installation will follow standard Salesforce managed package installation procedures. | Configuration | • Given the Sandbox environment is ready, When BusinessConnect package v10.147 is installed, Then the package should be successfully installed with all components • Given the package is installed, When the Credit & Collections Admin tab is accessed, Then all BusinessConnect configuration options should be visible
US-003 | As a Credit Administrator, I want to configure Equifax data providers with secure credentials and service endpoints so that the system can connect to Equifax services for credit reporting | This story covers configuration of four Equifax data providers: Equifax (commercial), Equifax Apigee (business verification), Equifax Business Principal Report, and Equifax Canada. Includes setting up User IDs, Security Codes, Service URLs, and timeouts. Dependencies: US-002 must be completed. Assumptions: Equifax will provide credentials via secure email at UAT time. All credentials must be protected per BusinessConnect security guidelines. | Configuration | • Given BusinessConnect is installed, When the Equifax data provider is configured with User ID 999WM01393 and Security Code, Then the connection should be established to https://commercial-ppe-uat.equifax.com/sbepg • Given BusinessConnect is installed, When the Equifax Apigee data provider is configured with User ID 999WM01393, Then the connection should be established to https://api.uat.equifax.com • Given BusinessConnect is installed, When the Equifax Business Principal Report data provider is configured, Then the data provider should use the Equifax connection settings • Given BusinessConnect is installed, When the Equifax Canada data provider is configured with User ID 999WM00178 and Subscriber Code 7007, Then the connection should be established to https://api.uat.equifax.ca • Given all data providers are configured, When the service timeout is set to 120 seconds, Then all API calls should respect this timeout
US-004 | As a Credit Administrator, I want to configure Data Provider Products for Equifax reports so that specific credit report types can be pulled from Equifax services | This story covers configuration of five Data Provider Products: Equifax Business Verification Report (RPT0042), Equifax Commercial BCIR2.0 (RPT0036) with Non Fi OneScore (SCR2037), Equifax Commercial Business Principal Report (BPR) (RPT2001) with Fico10, Equifax Commercial Canada with Score, and Equifax Business TIN Match. Includes setting up product option packages, days valid settings, and report data storage options. Dependencies: US-003 must be completed. Assumptions: Product codes and configurations follow Equifax STS development guide specifications. | Configuration | • Given the Equifax Apigee data provider is configured, When the Equifax Business Verification product is set up, Then the product should be available for report pulls • Given the Equifax data provider is configured, When the Equifax Commercial Credit product is configured with BCIR2.0+ with OneScore 2037 option package, Then the product should include ProductCode RPT 0036 and SCR 2037 • Given the Equifax data provider is configured, When the Equifax Business Principal Report product is configured with BPR option package, Then the product should include ProductCode RPT 2001 • Given the Equifax Canada data provider is configured, When the Equifax Canada Commercial Credit product is set up, Then the product should be available for Canadian credit reports • Given the Equifax Apigee data provider is configured, When the Equifax Business TIN Match product is set up, Then the product should be available for TIN verification
US-005 | As a Salesforce Administrator, I want to create custom fields on the Account object so that business verification data and credit decisions can be captured and displayed | This story covers creation of 13 custom fields on the Account object: Business Name (text), BillingStreet (text area), BillingCity (text), BillingState (text), BillingPostalCode (text), BillingCountry (picklist), Tax Id (text), Owner First Name (text), Owner Last Name (text), Decision Flag (text), BVS Decision (text), BVI Score (numeric), and Fraud Alert Score (numeric). Dependencies: US-002 must be completed. Assumptions: Field API names follow naming convention with __c suffix. Field-level security will be configured according to user profiles. | Configuration | • Given the Account object is accessible, When the Business Name field (Business_Name__c) is created as text type, Then the field should be available on Account records • Given the Account object is accessible, When billing address fields (BillingStreet, BillingCity, BillingState, BillingPostalCode, BillingCountry) are created, Then all address fields should be available for data entry • Given the Account object is accessible, When the Tax Id field (BVS_Tax_ID__c) is created as text type, Then the field should be available on Account records • Given the Account object is accessible, When owner name fields (Owner_First_Name__c, Owner_Last_Name__c) are created as text type, Then both fields should be available on Account records • Given the Account object is accessible, When the Decision Flag field (Decision_Flag__c) is created as text type, Then the field should accept values like 'charge card account' or 'trade credit account' • Given the Account object is accessible, When the BVS Decision field (BVS_Decision__c) is created as text type, Then the field should accept values 'Approve', 'Manual Review', or 'Decline' • Given the Account object is accessible, When score fields (BVI_Score__c, Fraud_Alert_Score__c) are created as numeric type, Then both fields should accept numeric values
US-006 | As a Credit Analyst, I want three manual buttons on the Account page to pull different types of credit reports so that I can review credit information on demand | This story covers configuration of three buttons in BusinessConnect: 'Review Credit' button to pull BCIR 2.0/Canada Commercial reports, 'Review BPR' button to pull Equifax Business Principal Reports (BPR), and 'Business Verification' button to pull Business Verification reports. Dependencies: US-004 and US-005 must be completed. Assumptions: Users must select applicable credit policy before initiating manual report pulls. Decision Flag must equal 'Trade Credit Account' for manual pulls. Training on this functionality will be provided as part of SOW. | Development | • Given an Account record is open and a credit policy is selected, When the 'Review Credit' button is clicked, Then the system should pull BCIR 2.0 or Canada Commercial report based on the selected policy • Given an Account record is open and a credit policy is selected, When the 'Review BPR' button is clicked, Then the system should pull an Equifax Business Principal Report • Given an Account record is open and Decision Flag equals 'Trade Credit Account', When the 'Business Verification' button is clicked, Then the system should pull a Business Verification report • Given an Account record is open and no credit policy is selected, When any manual report button is clicked, Then the system should display an error message prompting policy selection
US-007 | As a Credit Administrator, I want to configure two Credit Policies for Equifax Commercial and Equifax Canada so that appropriate credit products are used for different account types | This story covers configuration of two credit policies: 'Equifax Commercial' (Default Policy) for pulling Equifax Commercial Credit and Equifax Business Principal Reports (BPR), and 'Equifax Canada' for pulling Equifax Canada Commercial Credit Reports. Includes setting up verification, credit prequalification, and credit review product associations. Dependencies: US-004 must be completed. Assumptions: Credit policies will be selectable by users before manual report pulls. | Configuration | • Given Data Provider Products are configured, When the 'Equifax Commercial' credit policy is created, Then it should be marked as the Default Policy • Given the 'Equifax Commercial' policy exists, When the verification setup is configured, Then it should use Equifax Commercial Credit product • Given the 'Equifax Commercial' policy exists, When the credit prequalification setup is configured, Then it should use Equifax Business Principal Report product with BPR option package • Given the 'Equifax Commercial' policy exists, When the credit review setup is configured, Then it should use Equifax Commercial Credit product with BCIR2.0+ with OneScore 2037 option package • Given Data Provider Products are configured, When the 'Equifax Canada' credit policy is created, Then it should be available for selection • Given the 'Equifax Canada' policy exists, When the verification setup is configured, Then it should use Equifax Canada Commercial Credit product
US-008 | As a Credit Analyst, I want credit reports to be displayed in designated sections on the Account page so that I can easily access and review different report types | This story covers configuration of report objects to display in four sections: Equifax Business Verification Reports (for BVS), Equifax Commercial Reports (for BCIR2.0+), Equifax Blended Reports (for BPR), and Equifax Commercial Canada Reports (for Canada reports). Dependencies: US-004 and US-005 must be completed. Assumptions: Report sections will be added to Account page layout using related lists. | Configuration | • Given a Business Verification report is pulled, When the Account page is viewed, Then the report should be visible in the Equifax Business Verification Reports section • Given a BCIR2.0+ report is pulled, When the Account page is viewed, Then the report should be visible in the Equifax Commercial Reports section with OneScore displayed • Given a BPR report is pulled, When the Account page is viewed, Then the report should be visible in the Equifax Blended Reports section • Given a Canada report is pulled, When the Account page is viewed, Then the report should be visible in the Equifax Commercial Canada Reports section
US-009 | As a system, I want to configure a Business Verification scorecard with decision rules based on BVI Score and Fraud Alert Score so that automated credit decisions can be rendered | This story covers configuration of a Business Verification scorecard in BusinessConnect with rules based on BVI Score and Fraud Alert Score from the Business Verification report. Decision matrix: BVI 80-100 & Fraud Alert >=201 = Auto Approve; BVI 80-100 & Fraud Alert <=200 = Manual Review; BVI 80-100 & Fraud Alert null = Manual Review; BVI 50-79 & Fraud Alert >=201 = Manual Review; BVI 50-79 & Fraud Alert <=200 = Manual Review; BVI 50-79 & Fraud Alert null = Manual Review; BVI <50 & Fraud Alert >=201 = Manual Review; BVI <50 & Fraud Alert <=200 = Manual Review; BVI <50 & Fraud Alert null = Decline. Dependencies: US-005 must be completed. Assumptions: Scorecard will execute after Business Verification report is pulled. Score field names from report will be mapped to Account fields. | Development | • Given a Business Verification report is completed, When BVI Score is between 80-100 and Fraud Alert Score is greater than or equal to 201, Then BVS Decision should be set to 'Auto Approve' • Given a Business Verification report is completed, When BVI Score is between 80-100 and Fraud Alert Score is less than or equal to 200, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is between 80-100 and Fraud Alert Score is null, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is between 50-79 and Fraud Alert Score is greater than or equal to 201, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is between 50-79 and Fraud Alert Score is less than or equal to 200, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is between 50-79 and Fraud Alert Score is null, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is less than 50 and Fraud Alert Score is greater than or equal to 201, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is less than 50 and Fraud Alert Score is less than or equal to 200, Then BVS Decision should be set to 'Manual Review' • Given a Business Verification report is completed, When BVI Score is less than 50 and Fraud Alert Score is null, Then BVS Decision should be set to 'Decline'
US-010 | As an ERP system (MM2.0), I want to invoke Salesforce via API to create Account records and receive credit decisions so that the credit approval process is automated | This story covers the automated API integration flow where MM2.0 invokes Salesforce to create Account records, Salesforce performs internal validations, pulls credit reports, executes scorecard, and syncs Account ID, Decision, BVI Score, and Fraud Alert Score back to ERP. Detailed flow logic is documented in 'mSupply BusinessConnect API Integration Design Document' including authentication, error handling, and request/response payloads. Dependencies: US-005, US-006, US-009 must be completed. Assumptions: API integration design document reviewed and approved by client within first week after project kickoff. MM2.0 will handle API authentication and error responses. | Development | • Given MM2.0 sends a valid API request with business information, When Salesforce receives the request, Then a new Account record should be created with the provided data • Given an Account record is created via API, When internal validations pass, Then the system should automatically pull the Business Verification report • Given a Business Verification report is pulled, When the scorecard executes, Then BVI Score, Fraud Alert Score, and BVS Decision should be populated on the Account • Given the scorecard execution is complete, When the API response is sent, Then it should include Account ID, BVS Decision, BVI Score, and Fraud Alert Score • Given MM2.0 sends an invalid API request, When Salesforce receives the request, Then an appropriate error message should be returned with error details
US-011 | As a Salesforce Administrator, I want to provision remaining BusinessConnect licenses so that all users have appropriate access to the system | This story covers provisioning of remaining Salesforce licenses per SOW: 8 Credit User licenses, 2 API licenses, and 10 Sandbox licenses (in addition to 2 Admin licenses from US-001). Dependencies: US-001 must be completed. Assumptions: License allocation will follow Salesforce standard procedures. Users will be assigned licenses based on their roles. | Configuration | • Given the Production org is ready, When 8 Credit User licenses are provisioned, Then all 8 licenses should be active and assignable • Given the Production org is ready, When 2 API licenses are provisioned, Then both licenses should be active and assignable for API integration • Given the Sandbox is ready, When 10 Sandbox licenses are provisioned, Then all 10 licenses should be active and assignable
US-012 | As an Ascendion Quality Assurance team member, I want all test cases to be reviewed and signed off by the Business Analyst before deployment so that quality standards are met | This enterprise mandate ensures that all test cases undergo mandatory review and BA signoff before any deployment proceeds. This is a governance requirement separate from functional development. Dependencies: All functional user stories must be completed. Assumptions: BA will have access to all test cases and test results. Signoff process will be documented. | Governance | • Given all test cases are executed, When the BA reviews test results, Then the BA must provide written signoff before deployment • Given test cases fail review, When issues are identified, Then development must address issues before re-submission for BA signoff
US-013 | As a development team member, I want advance notification from the Equifax admin for planned configuration changes so that I can prepare for and coordinate the changes | This enterprise mandate ensures that the Equifax admin provides advance notification for any planned configuration changes to minimize disruption and ensure proper coordination. Dependencies: None. Assumptions: Notification will include change details, timing, and potential impact. | Governance | • Given a configuration change is planned, When the Equifax admin schedules the change, Then advance notification must be sent to the development team with change details and timing
US-014 | As a development team member, I want final code review support and coding signoff from the Equifax team so that code quality and best practices are validated | This enterprise mandate ensures that the Equifax team provides final code review support and signoff for all custom code before deployment. Dependencies: All development user stories must be completed. Assumptions: Equifax team will review code against BusinessConnect best practices and Salesforce standards. | Governance | • Given all custom code is developed, When the Equifax team reviews the code, Then the Equifax team must provide written signoff before deployment • Given code fails review, When issues are identified, Then development must address issues before re-submission for Equifax signoff
US-015 | As a testing team member, I want production-like test data covering all scenarios from the Equifax team so that comprehensive testing can be performed | This enterprise mandate ensures that the Equifax team provides production-like test data covering all testing scenarios including various BVI Score ranges, Fraud Alert Score ranges, and decision outcomes. Dependencies: US-003 and US-004 must be completed. Assumptions: Test data will include edge cases and cover all scorecard decision paths. | Governance | • Given UAT is ready to begin, When test data is requested, Then the Equifax team must provide production-like test data covering all scenarios • Given test data is provided, When testing is performed, Then the test data must cover all scorecard decision paths including Auto Approve, Manual Review, and Decline outcomes
US-016 | As a deployment team member, I want to execute a validated deployment process with post-deployment verification so that the solution is successfully moved to production | This story covers release readiness validation, deployment execution from Sandbox to Production, and post-deployment verification checks including smoke testing, data provider connectivity, report pulls, scorecard execution, and API integration testing. Dependencies: All functional, development, and governance user stories must be completed. Assumptions: Deployment will follow Salesforce change set or metadata API deployment process. Rollback plan will be prepared before deployment. | Deployment | • Given all user stories are completed and signed off, When release readiness is validated, Then deployment checklist must be completed and approved • Given deployment is ready, When the deployment is executed from Sandbox to Production, Then all components must be successfully deployed without errors • Given deployment is complete, When post-deployment verification is performed, Then smoke testing must confirm all key functionality works • Given deployment is complete, When data provider connectivity is tested, Then all Equifax connections must be verified in Production • Given deployment is complete, When manual report pulls are tested, Then all three report buttons must successfully pull reports • Given deployment is complete, When scorecard execution is tested, Then decisions must be correctly calculated based on scores • Given deployment is complete, When API integration is tested, Then the MM2.0 to Salesforce integration must successfully create accounts and return decisions
US-017 | As a Project Manager, I want a comprehensive deployment guide document provided to the client so that the deployment process is clearly documented and repeatable | This story covers creation and delivery of a deployment guide document to the client including deployment steps, validation procedures, rollback procedures, and post-deployment checklist. Dependencies: US-016 must be completed. Assumptions: Document will be provided in standard format and reviewed with client. | Deployment | • Given the deployment is complete, When the deployment guide is created, Then it must include all deployment steps and validation procedures • Given the deployment guide is created, When it is delivered to the client, Then the client must acknowledge receipt and understanding